AFENET Secretariat

Lugogo House, Ground Floor (Wings B&C)

Plot 42, Lugogo By-Pass

P.O BOX 12874, Kampala, Uganda

Tel: +256 417 700 650

Fax: +256 312 265 595

www.afenet.net

January 30, 2026

PROCUREMENT REFERENCE NUMBER: AFENET/SEC / RFP/2026/01/001

# REQUEST   FOR PROPOSAL: INDIVIDUAL/TEAM CONSULTANCY SERVICE TO EVALUATE PopCAB IMPLEMENTATION IN KENYA, TANZANIA, AND UGANDA

INTRODUCTION

Established in 2005, the African Field Epidemiology Network (AFENET) is a non-profit networking and service alliance of Field Epidemiology (and Laboratory) Training Programs (FELTPs), and other applied epidemiology training programs. AFENET is dedicated to helping ministries of Health in Africa build strong, effective, sustainable programs and capacity to improve public health systems on the continent.

AFENET, in collaboration with the US CDC, is seeking an individual/team of consultants with relevant training and professional experience to conduct an evaluation of PopCAB implementation in Kenya, Tanzania and Uganda. The anticipated duration of the consultancy is 35 consultancy days spread over 4 months (March- June 2026).

# BACKGROUND

Population Connectivity Across Borders (PopCAB) is a participatory methodology used to characterize population movement patterns and connectivity to inform public health decision making for preparedness, readiness, and response to public health threats. Further information on PopCAB can be found at the PopCAB tool kit and in the manuscript which can be found here and also attached to the advert.

PopCAB has been implemented in Kenya, Tanzania, and Uganda to support cross-border health security, outbreak preparedness, and surveillance planning. As PopCAB has expanded across multiple countries in East Africa, it is essential to systematically evaluate how the approach has been implemented, determine the extent to which findings have informed timely public health action, and identify opportunities to improve efficiency and impact. This evaluation will provide evidence to guide future PopCAB implementation and strengthen its contribution to public health decision-making at national and regional levels.

It is against this background that AFENET seeks to hire an individual/team of consultants to evaluate PopCAB Implementation in Kenya, Tanzania, and Uganda

PURPOSE  OF THE CONSULTANCY

The purpose of this evaluation is to review PopCAB implementation in Kenya, Tanzania, and Uganda during the 2023-2025 period; assess the extent to which findings were used to inform public health action; and identify opportunities to improve the PopCAB process for greater efficiency, effectiveness, and impact

SCOPE OF WORK

The consultant will perform the following tasks:

- Describe PopCAB implementation, outputs and capacity building impact: Compile and summarize PopCAB activities across countries by documenting implementation context, objectives, timelines, stakeholders, and geographic scope; assess how PopCAB was used in outbreak response and non-outbreak settings and its contribution to strengthening health worker skills; review key outputs and resource requirements; and compare implementation approaches, highlighting strengths, challenges, and lessons learned.

- Assess use of PopCAB findings for public health action: Examine how PopCAB findings informed public health actions at national and regional levels; identify key enablers and barriers to the use of findings and recommendations; and evaluate the extent to which these align with   security priorities.

- Analyze and synthesize cross-country findings: Conduct a comparative analysis across Kenya, Tanzania, and Uganda to identify common themes, differences, and lessons learned; highlight best practices and areas for improvement across all stages of implementation.

- Conduct stakeholder engagement and validation of findings: Facilitate remote/virtual validation workshops with stakeholders from Kenya, Tanzania, and Uganda to review preliminary findings; incorporate stakeholder feedback to refine conclusions and strengthen recommendations

METHODOLOGY

The evaluation will employ a qualitative approach, with activities conducted virtually, including:

- Document review: PopCAB workplans/concept notes, training plans and materials, reports, maps, and other related documentation from Kenya, Tanzania, and Uganda.

- Virtual key informant interviews: Conduct interviews with implementers, government officials, cross-border health actors, and partner organizations to gather insights on implementation and use of findings.

- Comparative analysis: Perform a cross-country synthesis to identify themes, variations, and lessons learned.

- Virtual validation workshops: Facilitate structured stakeholder workshops to validate preliminary findings and refine recommendations.

EXPECTED OUTCOMES

- Enhanced understanding of PopCAB’s value, limitations, and operational relevance within the East African context.

- Actionable recommendations to improve the efficiency, effectiveness, and impact of PopCAB implementation.

- Strengthened regional collaboration and harmonized approaches for cross-border population mapping and health security.

EXPECTED DELIVERABLES

| Deliverable | Consultancy days | Estimated time frame |
| --- | --- | --- |
| Inception report outlining the evaluation approach, tools, timeline, and workplan | 2 | March |
| Desktop document review | 10 | March |
| Approved data collection tools and completed virtual key informant interviews | 5 | April - May |
| A consolidated evaluation and comparative report describing PopCAB implementation across Kenya, Tanzania, and Uganda, highlighting similarities, differences, lessons learned, and the use of findings for public health action. | 15 | April - May |
| Validation workshop/Virtual oral presentation | 3 | June |

DURATION OF ENGAGEMENT:

The consultancy is expected to be completed over 4 months, inclusive of data collection, analysis, validation, and reporting. The level of effort is estimated at 35 consultancy days, with expected deliverables as indicated above

DUTY STATION:

The consultant will conduct the assignment in  remotely  in  3 countries (Uganda, Kenya, and Tanzania ),and we  donot  anticipate  any  travels  to  the  three  countries

REPORTING LINES

The consultant will report to the project coordinator at the AFENET secretariat and work closely with country focal points and the US CDC. Regular progress updates will be provided throughout the consultancy period to ensure that ongoing work is aligned with the purpose of the consultancy.

QUALIFICATION AND EXPERIENCE

The ideal candidate for this consultancy should possess  the  following;

Required Qualifications

- Advanced degree in public health, epidemiology, social sciences, anthropology, or a related field.

- Academic training on public health evaluation

- Familiarity with East African public health systems and cross-border health dynamics.

- Strong analytical, writing, and communication skills.

Required experience

- Experience conducting qualitative research

- Demonstrated experience conducting qualitative evaluations or assessments.

- Demonstrated experience in conducting public health evaluations

- Experience working in limited resource settings is an added advantage

Language requirements

Fluency in spoken and written English is mandatory while a working knowledge of Kiswahili is an added advantage

PERFORMANCE CRITERIA

The performance of the consultant will be evaluated bi-weekly, with the following criteria:

- Timely implementation of activities.

- Ability to meet deadlines in terms of reporting.

- Quality of the implementation of the assigned tasks

EVALUATION AND QUALIFICATION CRITERIA

- General educational qualification and relevant training (20 points)

- Experience related to the assignment (20 points)

- Detailed and applicable responses to the objectives and deliverables of the consultancy (35 points)

- Detailed Budget (10 points)

- Detailed work plan (10 points)

- Language skills (5 Points)

INTERESTED CANDIDATES ARE REQUESTED TO SUBMIT THE FOLLOWING DOCUMENTS TO AFENET FOR CONSIDERATION:

a)	Technical proposal not exceeding 5 pages on:

•	Understanding and interpretation of the Terms of Reference for the consultancy

•	Workplan, time, and activity schedule for the deliverables

•	Budget for the Consultancy

b)	Curriculum Vitae of the Consultant as well as the CV of any other individuals supporting the consultant

c)        Capacity statement

•	Including relevant experience related to the assignment (include samples of two most recent similar works and/or references for the same)

•	Contacts of at least three organizations previously worked for

INVITATION

AFENET invites eligible and qualified individuals to indicate their interest in providing the services. Applicants should provide information demonstrating that they have the required qualifications and relevant experience to perform the services.

Further information can be obtained by sending an inquiry to secprocurement@afenet.net. and copy  skyambadde@afenet.net

RESPONSE TO THE CALL

Electronic submission of the applicant’s resume, Expression of Interest letter, and relevant documentation should be submitted to  secprocurement@afenet.net and copied to skyambadde@afenet.net

The deadline for receipt of proposals is Friday  February  13,2026- 17;00hrs GMT.

Please click the link below   to access the Standard Forms and additional information on PopCAB

*ONLY successful candidates shall be contacted for an interview.

.